## Assumptions
AWDS MetroLink — Construction Stage Resourcing, FTE & Cost Model
Assumptions & basis of estimate. Edit the gold cells on the 'Rates' tab — all sheets and the total cost update automatically.
KEY ASSUMPTIONS
Construction-stage durations
• Management team | 36 months
• Contract Managers (and their delivery team) | 18 months
• Support staff | 18 months
• Designers (reachback) | 18 months
Number of contract packages / Contract Managers | 16 (one per package — see note 1)
Rates & hours | See the 'Rates' tab (editable).
DEFINITIONS
FTE | 1.0 FTE = one full-time-equivalent person at 100% utilisation.
Utilisation % | Share of a person's time spent on AWDS construction-stage work.
FTE (modelled)
Effort (person-months)
Effort (person-years)
Cost (€)
FTE vs NON-FTE TREATMENT
Management team & Contract Managers | Dedicated FTE — charged at the Management rate.
Support staff | Shared / part-time — charged at the Support rate.
Designers | Reachback / part-time — charged at the Designer rate.
SCOPE CONTEXT (drives the team make-up)
At construction stage the Contract Managers and their teams are NOT site supervision. Their remit is:
• Raising / tracking / closing RFIs
• Reviewing contractor design proposals
• Progress, design and coordination meetings; occasional site visits
• Meetings with utility asset owners
• Updating and managing the as-built drawings / CDE
• NEC contract administration, change and reporting
NOTES
1. Contract Manager headcount is taken from the management org chart (16). In practice some packages are
combined under a single Contract Manager (e.g. M140 & M146), so the dedicated CM count may be lower —
edit the headcount on sheet 1 to suit.
2. Cost is labour only — excludes expenses, fee/overhead uplift and inflation.
3. Management team excludes the Procurement Lead (procurement complete by construction stage).

## Rates
Rates & Cost Inputs
Edit the gold cells below. Every sheet and the total cost recalculate automatically.
Hours per person-month | 160 | Working hours used to convert person-months to chargeable hours
Management rate (€/hr) | 110 | Applies to the Management Team and Contract Managers (FTE)
Support staff rate (€/hr) | 50 | Applies to all Support Staff (interface, back-office & contract delivery support)
Designer rate (€/hr) | 95 | Applies to the Designers (reachback) team
Indicative total construction-stage cost (€)
(labour only — see Assumptions)

## Summary
Construction Stage — Resource & Cost Summary
Roll-up of all categories. Cost is driven by the editable 'Rates' tab.
Category | Type | Headcount | FTE (modelled) | Duration (months) | Effort (person-months) | Effort (person-years) | Cost (€)
Management Team | FTE (dedicated) |  |  | 36
Contract Managers | FTE (dedicated) |  |  | 18
Contract Delivery Support | Utilisation |  |  | 18
Project Support (Interface & Back-Office) | Utilisation |  |  | 18
Designers (reachback) | Utilisation |  |  | 18
TOTAL — Construction Stage
FTE (Management + Contract Managers)
FTE-equivalent (Support + Designers)

## 1 · Mgmt & Contract Mgrs
1 · Management Team & Contract Managers — FTE
Dedicated full-time-equivalent resource. Charged at the Management rate (Rates tab).
Role | Headcount | Utilisation % | FTE | Duration (months) | Effort (person-months) | Effort (person-years) | Cost (€) | Basis / notes
MANAGEMENT TEAM (36 months)
AWDS Project Director | 1 | 25% |  | 36 |  |  |  | Part-time senior oversight & governance
AWDS Project Management Lead | 1 | 100% |  | 36 |  |  |  | Full-time; leads delivery across all packages
AWDS Deputy Project Manager | 1 | 100% |  | 36 |  |  |  | Full-time; daily operations & coordination
AWDS Design Management Lead | 1 | 100% |  | 36 |  |  |  | Full-time; design integration & reachback mgmt
AWDS PMO Lead | 1 | 100% |  | 36 |  |  |  | Full-time; controls, reporting, information mgmt
AWDS Technical Delivery Lead | 1 | 100% |  | 36 |  |  |  | Full-time; technical assurance & verification
AWDS Commercial Lead | 1 | 100% |  | 36 |  |  |  | Full-time; NEC commercial & change
AWDS Cost Management Lead | 1 | 100% |  | 36 |  |  |  | Full-time; cost control & forecasting
Subtotal — MANAGEMENT TEAM (36 months)
CONTRACT MANAGERS (18 months)
AWDS Contract Manager (one per package) | 16 | 100% |  | 18 |  |  |  | Package PM: RFIs, contractor & utility-owner meetings, design-proposal review, as-builts, NEC admin
Subtotal — CONTRACT MANAGERS (18 months)
TOTAL

## 2 · Support Staff
2 · Support Staff — utilisation-based (non-FTE)
Shared / part-time resources. Charged at the Support rate (Rates tab).
Role | Headcount | Utilisation % | FTE | Duration (months) | Effort (person-months) | Effort (person-years) | Cost (€) | Basis / notes
CONTRACT DELIVERY SUPPORT (team around the Contract Managers, 18 months)
Contracts / Technical Engineer | 8 | 75% |  | 18 |  |  |  | Reviews contractor design proposals, raises/closes RFIs, technical correspondence (~1 per 2 packages)
Document Controller / As-Built Coordinator | 4 | 60% |  | 18 |  |  |  | Manages & updates as-built drawings and CDE (~1 per 4 packages)
Quantity Surveyor / Commercial Support | 4 | 60% |  | 18 |  |  |  | NEC change, valuations and payment support (~1 per 4 packages)
Utilities Liaison Coordinator | 2 | 50% |  | 18 |  |  |  | Meetings & coordination with utility asset owners
CEMP / Environmental Coordinator | 2 | 40% |  | 18 |  |  |  | Environmental compliance and CEMP across packages
Planner / Scheduler (package) | 2 | 50% |  | 18 |  |  |  | Programme tracking at package level
Subtotal — CONTRACT DELIVERY SUPPORT (team around the Contract Managers, 18 months)
PROJECT SUPPORT — Interface & Back-Office (18 months)
BIM Manager | 1 | 50% |  | 18 |  |  |  | Shared across programme
Deputy BIM Manager | 1 | 50% |  | 18
Information Manager | 1 | 50% |  | 18
Deputy Information Manager | 1 | 40% |  | 18
Senior GIS Consultant | 1 | 30% |  | 18 |  |  |  | On-demand
Senior GIS Analyst | 1 | 40% |  | 18
Surveys Coordinator | 1 | 30% |  | 18 |  |  |  | Ad-hoc survey requests
CDE Document Controller (project) | 1 | 70% |  | 18 |  |  |  | Project-wide CDE
BusConnects Interface | 1 | 20% |  | 18 |  |  |  | Interface management
DAA Interface | 1 | 20% |  | 18 |  |  |  | Interface management
UAO Engagement Team | 2 | 30% |  | 18 |  |  |  | Utility/asset-owner engagement
Administrator | 2 | 80% |  | 18 |  |  |  | Team & document admin
Health & Safety Advisor | 1 | 50% |  | 18 |  |  |  | CDM / safety in design support
QA / QC Manager | 1 | 50% |  | 18 |  |  |  | Quality assurance
Risk Manager | 1 | 30% |  | 18
Project Controls Analyst | 1 | 60% |  | 18 |  |  |  | Reporting & dashboards
HR & People Coordinator | 1 | 25% |  | 18
IT / Systems Support | 1 | 25% |  | 18
Communications & Stakeholder Liaison | 1 | 30% |  | 18
Training & Competency Coordinator | 1 | 20% |  | 18
Office Manager | 1 | 60% |  | 18
Subtotal — PROJECT SUPPORT — Interface & Back-Office (18 months)
TOTAL

## 3 · Designers
3 · Designers — reachback, utilisation-based (non-FTE)
Design discipline reachback team. Charged at the Designer rate (Rates tab).
Role | Headcount | Utilisation % | FTE | Duration (months) | Effort (person-months) | Effort (person-years) | Cost (€) | Basis / notes
DESIGN REACHBACK TEAM (18 months)
Design Management / Coordination | 1 | 30% |  | 18 |  |  |  | Coordinates reachback requests
Utilities South | 3 | 25% |  | 18 |  |  |  | Reachback — design queries & proposal review
Sustainability | 2 | 15% |  | 18 |  |  |  | On-demand
Land Access | 2 | 20% |  | 18 |  |  |  | On-demand
Structures | 2 | 25% |  | 18 |  |  |  | Design review & RFI support
Heritage | 1 | 10% |  | 18 |  |  |  | On-demand
Cellars & Playing Pitches | 1 | 10% |  | 18 |  |  |  | On-demand
Archaeology | 1 | 15% |  | 18 |  |  |  | On-demand
Biodiversity | 1 | 10% |  | 18 |  |  |  | On-demand
Env. Monitoring | 2 | 20% |  | 18 |  |  |  | Periodic monitoring
Subtotal — DESIGN REACHBACK TEAM (18 months)
TOTAL