## Executive Dashboard
[14 empty] | StageNo | StageName | Phase | StageCount | Status | StatusCount
METROLINK | [13 empty] | 0 | Not Yet Started | Not Started |  | Not Started
[14 empty] | 1 | Pre-IDC Pack Issued | Design Development → Tender |  | In Progress
Design-to-Tender Workflow — Pack Status Summary (02 July 2026) | [13 empty] | 2 | IDC (Inter-Disciplinary Check) | Design Development → Tender |  | At Risk
[14 empty] | 3 | Full ITT Pack Issued – Rev 01 | Design Development → Tender |  | Delayed
[14 empty] | 4 | TII Instruction to Issue C01 | Design Development → Tender |  | Complete
[14 empty] | 5 | AWDS C01 Submission | Design Development → Tender
TOTAL CONTRACTS TRACKED |  | DESIGN DEVELOPMENT → TENDER |  | PROCUREMENT & AWARD |  | NOT YET STARTED |  | NEEDS ATTENTION |  | AVG. PIPELINE PROGRESS |  |  |  | 6 | Ready for Tender | Design Development → Tender
[14 empty] | 7 | ITT Issue Date | Design Development → Tender
[14 empty] | 8 | Tender Period | Procurement & Award
[14 empty] | 9 | ITT Award | Procurement & Award
[14 empty] | 10 | Contract Award | Procurement & Award
[14 empty] | 11 | Construction Start | Procurement & Award
Contract Tracker — All Contracts
Select a Stage No. and Status for every contract, DTW and Framework alike — the dashboard above updates automatically.
Group | Contract | Stage No. | DTW Stage | Phase | Status | Progress | Last Updated | Notes
M14 | M140 | 5 |  |  | In Progress |  | 2026-06-29 | AWDS C01 drawings submitted to TII for review
M14 | M141 | 1 |  |  | In Progress |  | 2026-06-25 | Preparing for IDC review
M14 | M142 | 1 |  |  | In Progress |  | 2026-06-25 | Preparing for IDC review
M14 | M145 | 5 |  |  | At Risk |  | 2026-06-30 | AWDS resourcing constraint – monitor submission date
M14 | M146 | 1 |  |  | In Progress |  | 2026-06-26 | Preparing for IDC review
M14 | M147 | 3 |  |  | Delayed |  | 2026-06-10 | Rev 01 issued – awaiting TII instruction to issue C01
M14 | M190 | 3 |  |  | In Progress |  | 2026-06-27 | Full ITT pack issued at Rev 01
M13 & M16 | M130 | 0 |  |  | Not Started |  | 2026-06-20 | Design pack in preparation
M13 & M16 | M135 | 3 |  |  | In Progress |  | 2026-06-28 | Full ITT pack issued at Rev 01
M13 & M16 | M138 | 0 |  |  | Not Started |  | 2026-06-20 | Design pack in preparation
M13 & M16 | M160 | 0 |  |  | Not Started |  | 2026-06-20 | Design pack in preparation
M13 & M16 | M161 | 0 |  |  | At Risk |  | 2026-06-30 | Start date at risk of slipping – awaiting design brief
Framework | M11 | 11 |  |  | In Progress |  | 2026-06-29 | Framework contract – ongoing works; stage mapped to Construction Start
Framework | Minor Works | 11 |  |  | In Progress |  | 2026-07-01 | Framework contract – multiple work orders in progress across the network
Framework | Baseline Monitoring | 11 |  |  | Complete |  | 2026-06-15 | Framework contract – baseline survey complete, monitoring ongoing
Framework | DAA | 9 |  |  | At Risk |  | 2026-06-30 | Framework contract – awaiting access agreement sign-off before award
Stage Map — Where Every Contract Sits Today
Each marker shows a contract's current stage, coloured by status. Updates live from the table above.
Contract | Group | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
M140 | M14
M141 | M14
M142 | M14
M145 | M14
M146 | M14
M147 | M14
M190 | M14
M130 | M13 & M16
M135 | M13 & M16
M138 | M13 & M16
M160 | M13 & M16
M161 | M13 & M16
M11 | Framework
Minor Works | Framework
Baseline Monitoring | Framework
DAA | Framework
Status: | Not Started | 0: In Progress; 1: At Risk; 2: Delayed; 3: Complete
Tip: use the column filters on the Contract Tracker table to drill into any status, group or stage. The reference lists behind the charts are grouped and hidden in columns R:Y — click the outline '+' above column R to expand.
Note on D58: Stage 0: Not Yet Started (Not Started)
Note on E58: Stage 1: Pre-IDC Pack Issued (Design Development → Tender)
Note on F58: Stage 2: IDC (Inter-Disciplinary Check) (Design Development → Tender)
Note on G58: Stage 3: Full ITT Pack Issued – Rev 01 (Design Development → Tender)
Note on H58: Stage 4: TII Instruction to Issue C01 (Design Development → Tender)
Note on I58: Stage 5: AWDS C01 Submission (Design Development → Tender)
Note on J58: Stage 6: Ready for Tender (Design Development → Tender)
Note on K58: Stage 7: ITT Issue Date (Design Development → Tender)
Note on L58: Stage 8: Tender Period (Procurement & Award)
Note on M58: Stage 9: ITT Award (Procurement & Award)
Note on N58: Stage 10: Contract Award (Procurement & Award)
Note on O58: Stage 11: Construction Start (Procurement & Award)